## Sheet1
Date | Time | Hours | Task
2024-02-23 | 9:00 | 1.5 | Worked on Project Proposal (Problem Definition)
2024-02-23 | 10:30 | 1 | Worked on Project Presentation (Problem Definition)
2024-03-04 | 7:00 | 1 | Making Playlists in Apple Music (Data Ingestion)
2024-03-05 | 17:00 | 2 | Making Playlists in Apple Music (Data Ingestion)
2024-03-06 | 18:30 | 2 | Making Playlists in Apple Music (Data Ingestion)
2024-03-11 | 16:30 | 3 | Making Playlists in Apple Music (Data Ingestion)
2024-03-12 | 16:30 | 3.5 | Making Playlists in Apple Music (Data Ingestion)
2024-03-13 | 19:30 | 1.5 | Grabbing song, artist, genre columns from playlists in ChatGPT (Data Preparation)
2024-03-14 | 5:30 | 1 | Grabbing song, artist, genre columns from playlists in ChatGPT (Data Preparation)
2024-03-14 | 9:30 | 1 | Grabbing song, artist, genre columns from playlists in ChatGPT (Data Preparation)
2024-03-14 | 10:30AM | 0.67 | Term Project Update (Word Doc)
2024-03-14 | 18:30 | 0.75 | Term Project Update (PowerPoint)
2024-03-24 | 3:30PM | 1 | Encoding Mood and Genre Labels to numbers
2024-03-24 | 4:30PM | 1 | Using the Kmeans Algorithm to Cluster data
2024-03-24 | 5:30PM | 2 | Lost CSV file data from computer crashing, have to remake a new one
2024-03-24 | 7:30PM | 1.5 | Figuring out which number went with each genre and mood
2024-03-24 | 9:00PM | 3 | GUI
2024-03-25 | 8:30AM | 2 | GUI
2024-03-25 | 10:30AM | 1.5 | Using the K Nearest Neighbors Algorithm to Cluster Data (This is better than Kmeans)
2024-03-26 | 8:30AM | 1.5 | Getting the output to be put into the GUI
2024-03-26 | 10:00AM | 5 | Researching and coding how to output only same mood but different genre
2024-03-31 | 8:00PM | 1 | Working on final project paper (Not done)
2024-04-10 | 11:00AM | 2 | Overall testing of code to make sure it works (Realized it did not work as originally intended)
2024-04-19 | 10:00AM | 2.5 | Trying different things to make the output how it was originally intended to work (did not work so kept the same)
2024-04-20 | 12:00PM | 2 | Finished final project paper
2024-04-21 | 8:00AM | 2 | Worked on Project Presentation
2024-04-21 | 1:00PM | 1 | Practicing Presentation
2024-04-21 | 5:00PM | 0.25 | Creating instructions for my code
2024-04-21 | 5:15PM | 2.5 | Realized I did not do the final paper correctly so I had to completely redo it
| Total Hours: | 50.67